## Effort Assessment
| Resource | Phase | FTE Effort Requirement | FTE Cost
Project Manager | Project Manager | Discovery Phase | 0.2 | 1333.3333
Project Manager |  | Planning and Business Case Phase | 1 | 13333.3333
Project Manager |  | Design Phase | 1 | 26666.6667
Project Manager |  | Delivery Phase | 0.6 | 12000
Project Manager |  | Testing Phase | 0.6 | 20000
Project Manager |  | Go Live | 0.4 | 5333.3333
Project Manager |  | Embedding and Remediation Phase | 0.2 | 1333.3333
Data Quality Architect | Data Quality Architect | Discovery Phase | 0.2 | 1333.3333
Data Quality Architect |  | Planning and Business Case Phase | 0.2 | 2666.6667
Data Quality Architect |  | Design Phase | 1 | 26666.6667
Data Quality Architect |  | Delivery Phase | 1 | 20000
Data Quality Architect |  | Testing Phase | 1 | 33333.3333
Data Quality Architect |  | Go Live | 0.6 | 8000
Data Quality Architect |  | Embedding and Remediation Phase | 0.2 | 1333.3333
Data Quality Developer(s) | Data Quality Developer(s) | Discovery Phase | 0 | 0
Data Quality Developer(s) |  | Planning and Business Case Phase | 0 | 0
Data Quality Developer(s) |  | Design Phase | 0.4 | 10666.6667
Data Quality Developer(s) |  | Delivery Phase | 2 | 40000
Data Quality Developer(s) |  | Testing Phase | 2 | 66666.6667
Data Quality Developer(s) |  | Go Live | 1 | 13333.3333
Data Quality Developer(s) |  | Embedding and Remediation Phase | 1 | 6666.6667
Data Quality Tester(s) | Data Quality Tester(s) | Discovery Phase | 0 | 0
Data Quality Tester(s) |  | Planning and Business Case Phase | 0 | 0
Data Quality Tester(s) |  | Design Phase | 0 | 0
Data Quality Tester(s) |  | Delivery Phase | 0.5 | 10000
Data Quality Tester(s) |  | Testing Phase | 1.5 | 50000
Data Quality Tester(s) |  | Go Live | 0 | 0
Data Quality Tester(s) |  | Embedding and Remediation Phase | 0 | 0
Business Users | Business Users | Discovery Phase | 1.5 | 10000
Business Users |  | Planning and Business Case Phase | 1 | 13333.3333
Business Users |  | Design Phase | 0.5 | 13333.3333
Business Users |  | Delivery Phase | 0 | 0
Business Users |  | Testing Phase | 1.5 | 50000
Business Users |  | Go Live | 1.5 | 20000
Business Users |  | Embedding and Remediation Phase | 1.5 | 10000
| Total Resource Costs |  |  | 487333.3333

## Phases
Phase Name | Phase Length (months) | FTE proportion | Total Phase Cost
Discovery Phase | 1 | 0.083333 | 12666.6667
Planning and Business Case Phase | 2 | 0.16667 | 29333.3333
Design Phase | 4 | 0.33333 | 77333.3333
Delivery Phase | 3 | 0.25 | 82000
Testing Phase | 5 | 0.41667 | 220000
Go Live | 2 | 0.16667 | 46666.6667
Embedding and Remediation Phase | 1 | 0.083333 | 19333.3333
487333.3333

## Role Details
Resource | Role Definition | Estimated FTE Cost | Project Cost | Day Rate | Effort (Days)
Project Manager | Status reporting, team co-ordination, plan management, issue and risk management | 80000 | 80000 | 320 | 250
Data Quality Architect | Requirements gathering and definition, design of solution, management of developers and testers | 80000 | 93333.3333 | 320 | 291.6667
Data Quality Developer(s) | Build of data quality rules, ETL processes and reports in chosen tool, testing, support of testing | 50000 | 137333.3333 | 200 | 686.6667
Data Quality Tester(s) | Testing of the data quality rules and management of defects from business users. | 40000 | 60000 | 160 | 375
Business Users | Active contribution to requirements, review of design, testing of data quality rules, sign offs. | 65000 | 116666.6667 | 260 | 448.7179
487333.3333

## Assumptions
Role | Assumptions
Project Manager | Discovery phase: The discovery work is led by the data quality lead for the company and the PM is only needed 1 day per week (0.2 FTE) to create the high level plan and start preparing for the planning phase. Planning and business case phase / Design phase: These phases require preparation of a detailed plan and co-ordination of business resources and developers/architects so will require a full time project manager (1 FTE) Development/Test Phases: The development phase requires less business and data quality team interaction and therefore less co-ordination work for the project manager, hence a reduction to 3 days per week (0.6 FTE). The test phases are overseen by the project manager, with support from the tester(s) and again 3 days per week is sufficient (0.6 FTE). Go Live / Embedding and Remediation Phases: These phases represent a hand off of the project to business as usual resources and the project management role is gradually ramped down to 2 (0.4 FTE) and then 1 day per week (0.2 FTE).
Data Quality Architect | Discovery / Planning and business case phases: This role is providing guidance and advice on data quality tools, required team and high level design in these phases - 1 day per week is sufficient (0.2 FTE). Design, Development and Test phases: This role is primarily responsible for the design and development phases and therefore is full time. The test phase is a busy period for this role as it manages resolution of all defects (1 FTE). Other phases: As the go live occurs, the role starts to ramp down - providing intensive support whilst the business gets used to using the data quality rules. (0.6 FTE in Go Live, 0.2 FTE during remediation phase)
Data Quality Developers | Managed by the Data Quality Architect, these roles (2 developers) are required to support the design process (0.4 FTE). After design, they ramp up to full time in the Development and Test phases (2 FTE). They will build data quality rules, ETL and reports and resolve defects identified. A reduced version of the team will need to be present to manage support issues after go live (1 FTE).
Data Quality Tester | Managed by the data quality architect, these roles exist to find issues with the data quality rules prior to business users being asked to test. As such they are critical towards the end of the development phase (0.5 FTE) and ramp up significantly through the test phase (1.5 FTE). In the test phase, they will also train and support business users on how to use the data quality tool and how to test rules.
Business User | A variety of business users will need to be involved in the initiative at different phases. The FTE count is an amalgamation of the expected effort. Discovery phase: 3 different team members (each representing a department) for 2.5 days per week each (1.5 FTE). Planning and business case phase: 3 team members for ~1.5 days per week to help determine business benefits for the business case (1 FTE) Design phase: 3 team members totalling 2.5 days per week of effort to review and sign off the design (0.5 FTE). Delivery phase: Business users are not required in this phase except for small points of clarification (0 FTE). Test phase: Business users required to test in the second half of the phase. Each tester may need up to 3 days per week for 2, but are not required in the first half of the test phase which is conducted internally by the team. (1.5 FTE) Other phases: During the go live and embeddnig and remedition phases, there is a significant effort required from business users to use the results of the data quality rules to make improvements to the data. This is a significant effort which should decrease over time as data reaches a higher standard and is maintained at this level. (1.5 FTE)

## Development Deliverables Calc
Rule Development Effort | Number of rules | Effort Per Rule (Days) | Effort in Total (Days)
Low | 75 | 2 | 150
Medium | 60 | 3 | 180
High | 25 | 6 | 150
Total Rule Development and Testing Effort |  |  | 480
Other Cost Estimates |  |  | Effort (Man Days)
ETL Effort |  |  | 240
Tool Set Up Activities |  |  | 100
Report Development |  |  | 250
Total "Other Cost" Effort |  |  | 590
Total Estimated Effort |  |  | 1070
Reconcile to Resource Estimates
Developer Effort in Plan |  |  | 686.6667
Tester Effort in Plan |  |  | 375
Total Effort Per Plan |  |  | 1061.6667

## Benefits Calculation Worked Eg
Data Quality Rule | Business Impact | Quantification of Benefit
Missing supplier email addresses for remittance advices | Suppliers contact finance to chase payment despite remittance having been sent | 120000
Detailed Calculation
Sub Calculation | Result | Calculation | Supporting Information
Typical Rate of Remittance Queries Per Invoice | 5% | 6,000/120,000 | - 6,000 remittance queries were raised in the last quarter against 120,000 supplier invoices (5%)
Expected Number of Remittance Queries Next Quarter | 7500 | 5% * 150,000 | - The number of invoices for the next quarter is expected to be 150,000.
Effort to Resolve Remittance Queries Next Quarter (Days) | 166.6667 | 7500*10 / (60*7.5) | - Each query takes 10 minutes to resolve on average. Each working day is 7.5 hours.
Annual Effort to Resolve Remittance Queries (Days) | 666.6667 | 167*4 | -Number of invoices and query percentage remains flat across the year if no action is taken.
Cost of this Effort Annually | 120000 | 45000/240 * 667 | -Annual cost of FTE in this role is 45,000, assume 240 working days per year.
Detailed Calculation
Sub Calculation | Result | Calculation | Supporting Information
Typical Rate of Remittance Queries Per Invoice | 5% | 6,000/120,000 | - 6,000 remittance queries were raised in the last quarter against 120,000 supplier invoices (5%)
Expected Number of Remittance Queries Next Quarter | 7500 | 5% * 150,000 | - The number of invoices for the next quarter is expected to be 150,000. | 1500
Effort to Resolve Remittance Queries Next Quarter (Days) | 166.6667 | 7500*10 / (60*7.5) | - Each query takes 10 minutes to resolve on average. Each working day is 7.5 hours. | 33.3333 | 133.3333
Annual Effort to Resolve Remittance Queries (Days) | 666.6667 | 167*4 | -Number of invoices and query percentage remains flat across the year if no action is taken. |  | 25000
Cost of this Effort Annually | 120000 | 45000/240 * 667 | -Annual cost of FTE in this role is 45,000, assume 240 working days per year.