## Sheet1
12000

## Sheet2
Month
Phase | Initiative Activity | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Design Phase | Greenlight to start
Tool Selection Finalised | bar: Month 0
Tool Setup (Development) | bar: Month 1
Detailed Requirements Gathering | bar: Month 0
Identify Data Quality Rules/Security Model | bar: Month 1 to Month 2
Design Documentation and Approvals | bar: Month 2 to Month 3
Design Approved
Delivery Phase | Connect to Data and Create ETL | bar: Month 4
Create Data Quality Rules | bar: Month 5 to Month 6
Unit Testing | bar: Month 6
Development Complete
Testing Phase | Create Test Documentation | bar: Month 5 to Month 6
End to End Test | bar: Month 7
User Acceptance Test | bar: Month 8
Test Documentation and Defect Resolution | bar: Month 9
Testing Complete
Go Live | Go - No Go Preparation and Meeting | bar: Month 9
Cutover and Pilot | bar: Month 10
Initiative Live
Embedding Phase | Roll Out and Post Go Live Support | bar: Month 11